## FY26 Contract Timeline
02.a.1. Draft FY26 Contract Timeline
Action | Responsibility | Dates | Details
Renewal application submitted | School | 2025-10-01
Trainings for renewing schools | CSD | 2025-11-05 | Introduce the contracting process, including Performance Framework (Options 1, 2 and 3) and mission specific goals and templates; Option 3 or new Option 2 templates must be identified 60 days before contract negotiations
Renewal hearings | PEC | Dec. 8-10, 2025
Email new and renewing schools | CSD | 2025-12-15 | Overview of contract process, Performance Framework options, documents needed, timeline, scheduling survey for appointments with CSD in preparation for documents due Jan. 26, 2026
PEC notice of renewal or non-renewal | PEC | 2025-12-15 | Any conditions of renewal will be included in renewal letter
Technical assistance webinar | CSD | 2026-01-05 | To review contract process and documents due in 3 weeks
Technical assistance appointments | CSD | Jan. 5-26, 2026 | Schools may request appointments with CSD staff as needed through Google form in 12/15/25 email or by contacting CSD
Initial contract preparation documents due | School RESPONSE NEEDED | 2026-01-26 | Contract preparation workbook including - Performance Framework option - interim assessments if Option 2 or 3 - mission and education program - proposed mission goal with rubric if needed - contacts to receive notice including attorneys and consultants - complete amendment forms for contract chagnes
Template preparation | CSD | 1/26/26 to 3/13/2026 | CSD to prepare a template for all Option 2 and 3 types not already prepared. No contracts finalized until the template is complete
Review of education programs, mission goals and rubrics | CSD | Jan. 27 - Feb. 10, 2026 | Meet with schools as needed to finalize education programs, goals and rubrics
Initial Contract preparation | CSD | Jan. 27 - Feb. 10, 2027 | a) Completion of spreadsheet with contract information b) Contacts, including attorneys and consultants c) Complete amendment forms for contract changes
Prepare and finalize negotiations drafts | PEC Vice Chair, Attorney, CSD | Feb. 10-24, 2026
Email HA, GC Chair and school attorney to review final contract documents | PEC Attorney | 2026-02-25
School confirm documents correct; final negotion draft complete: no changes until negotiation | School RESPONSE NEEDED | 2026-02-27 | Confirmation of information in contract documents
Documents sent to full negotiation teams | PEC Attorney | 2026-03-02 | All negotiation documents in folder ready for negotiations. Include rubrics and amendment forms for changes
Review final negotiation drafts | PEC Negotiation Subcommittee | March 3-10, 2026 | No changes to documents from this point until negotiations
Negotiations | CSD | March 10-13, 2026 (Tentative) | Negotiate all documents. Rubrics and background for the mission goal is kept in the negotiation folders as backup for their goal. The school may modify these during the term.
School to provide all Contract Section 2 in Epicenter | School: RESPONSE NEEDED | 2026-03-13 | School to upload all documents into Epicenter
Template completion | CSD | 2026-03-13 | CSD to prepare a template for all Option 2 and 3 types not already prepared. No contracts finalized until the template is complete
Final drafts to school | Attorney | By March 23, unless further negotiating meeting needed | Attorney and school to finalize documents. HA to schedule GC meeting and complete resolution of vote
School to review and confirm documents are correct | School: RESPONSE NEEDED | 2025-03-27 | Review and finalize document for GC vote
Governing council meeting and vote | School | no later than 1 week before PEC meeting
Final draft to PEC for vote | Attorney to EC for agenda | Week before PEC meeting | PEC to vote
PEC vote | PEC | 2026-04-17
Creation of complete contract | Attorney, CSD liaison and HA | April 20-24, 2026 | Attorney and CSD liaison to create full contract; Send to Chair and GC Chair for signature Finalize the pdf
Creation of Record of Performance | CSD | 2026-05-01 | Final executed contract and all administrative documents uploaded in Epicenter and posted on website; Option 2 and 3 templates on website; mission goal templates finalized and operational